## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | ExpandTesting Notes App — UI + API Hybrid Testing
Test Plan ID: | TP-NOTES-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Murari Aashrith
Approved By: | QA Engineer
SCOPE
Features to be Tested:
1. UI: Login and Authentication
2. UI: Create Note (Title, Description, Category)
3. UI: Notes List — Immediate Visibility Post-Creation
4. UI: Edit Note (Title, Description, Category Update)
5. UI: Delete Note (Confirmation Modal) | ☐
6. API: POST /users/login — Token Authentication | ☐
7. API: GET /notes — Fetch Notes List | ☐
8. API: POST /notes — Create Note via API | ☐
9. API: PUT /notes/{id} — Update Note via API
10. API: DELETE /notes/{id} — Delete Note via API
11. E2E: UI-Created Note Visible in API (UI → API Sync)
12. E2E: API-Deleted Note Absent from UI (API → UI Sync)
13. Negative: Invalid login, missing fields, unauth API calls
14. Performance: API response time < 2000ms, Page load < 5000ms
Start Date:
TESTING TYPE
Functional Testing | ☑
Regression Testing | ☐
Integration Testing | ☑
UAT | ☐
Test Data Provider:
TEST ENVIRONMENT
Environment: | QA / Staging
Browser/OS: | Chrome Latest, Firefox Latest / Windows 10+, macOS 13+
UI URL: | https://practice.expandtesting.com/notes/app
API Base URL: | https://practice.expandtesting.com/notes/api
API Tool: | Postman
TIMELINE
Start Date: | 06-05-2026
End Date: | 2026-05-07
RISKS & ASSUMPTIONS
Risks: | Public test environment shared with other users; token expiry mid-session; locator changes after deployments
Assumptions: | Test account is pre-registered; network is stable; API docs reflect current implementation
ENTRY CRITERIA
1. App deployed and accessible at test URL 2. QA test account registered and confirmed 3. Test cases reviewed and signed-off 4. Test environment verified (UI loads, API returns 200 for GET /notes)
EXIT CRITERIA
1. 100% Critical & High test cases executed 2. Zero open Critical defects 3. Test Summary Report delivered

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | UI Login — Valid | Verify a registered user can log in with correct email and password and is redirected to the Notes dashboard. | User account exists: testuser_capstone@example.com / Test@1234Secure
SC-002 | UI Login — Invalid Password | Verify login fails and an error message is displayed when wrong password is entered. | User account exists; browser on login page
SC-003 | UI Login — Empty Email | Verify the login form blocks submission and shows validation when email field is empty. | Browser open on login page
SC-004 | UI Login — Empty Password | Verify the login form blocks submission when the password field is left blank. | Browser open on login page
SC-005 | UI Login — Malformed Email | Verify login fails and error is shown when email format is invalid (e.g. missing @ symbol). | Browser open on login page
SC-006 | UI Login — Unregistered Account | Verify login fails with appropriate error when email is not registered in the system. | Email address has no account in the system
SC-007 | UI Create Note — Home Category | Verify authenticated user can create a note with category Home and it appears in list immediately. | User is logged in to Notes dashboard
SC-008 | UI Create Note — Work Category | Verify authenticated user can create a note with category Work and it appears in list. | User is logged in to Notes dashboard
SC-009 | UI Create Note — Personal Category | Verify authenticated user can create a note with category Personal and it appears in list. | User is logged in to Notes dashboard
SC-010 | UI Create Note — Empty Title | Verify the note creation form prevents submission when Title field is empty. | User is logged in; on Add Note form
SC-011 | UI Create Note — Empty Description | Verify the note creation form prevents submission when Description field is empty. | User is logged in; on Add Note form
SC-012 | UI Delete Note — Confirm Modal | Verify that clicking Delete on a note triggers a confirmation modal and note is removed on confirm. | User is logged in; at least one note exists
SC-013 | UI Delete Note — Cancel Modal | Verify that cancelling the delete confirmation modal preserves the note in the list. | User is logged in; at least one note exists
SC-014 | API Auth — Valid Login | Verify POST /users/login returns HTTP 200 and a valid x-auth-token with correct credentials. | Registered user account exists
SC-015 | API Auth — Invalid Credentials | Verify POST /users/login returns HTTP 401 with error message when credentials are wrong. | None — negative test
SC-016 | API Auth — No Token | Verify all protected API endpoints return HTTP 401 when no x-auth-token header is included. | None — unauthenticated request
SC-017 | API GET Notes — List | Verify GET /notes returns HTTP 200 and a JSON list of notes for authenticated user. | Valid auth token obtained via login
SC-018 | API Create Note — Valid | Verify POST /notes returns HTTP 200 and creates a note with matching fields. | Valid auth token available
SC-019 | API Create Note — Missing Title | Verify POST /notes returns HTTP 400 when title field is absent from request body. | Valid auth token available
SC-020 | API Create Note — Missing Description | Verify POST /notes returns HTTP 400 when description field is absent from request body. | Valid auth token available
SC-021 | API Delete Note — Valid | Verify DELETE /notes/{id} returns HTTP 200 and note no longer appears in GET /notes. | Valid auth token; note with known ID exists
SC-022 | API Delete Note — Already Deleted | Verify DELETE /notes/{id} returns HTTP 404 when the note was already deleted. | Valid auth token; note has been previously deleted
SC-023 | API GET Note by ID — Post Delete | Verify GET /notes/{id} returns HTTP 404 for a note that has been deleted. | Valid auth token; note deleted

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-001 | SC-001 | Login with valid credentials redirects to dashboard | Account exists: testuser_capstone@example.com / Test@1234Secure Browser open, cookies cleared | 1. Navigate to /notes/app/login 2. Enter email: testuser_capstone@example.com 3. Enter password: Test@1234Secure 4. Click Login button 5. Observe URL and page content | 1. URL changes to /notes/app (no /login) 2. Notes dashboard displayed 3. No error messages visible 4. User is authenticated | High | Not Started
TC-002 | SC-002 | Login with incorrect password shows error | Valid account exists Browser on /notes/app/login | 1. Navigate to login page 2. Enter valid email 3. Enter wrong password: WrongPass!999 4. Click Login 5. Observe response | 1. User remains on login page 2. Error alert is visible 3. No redirect to dashboard occurs 4. Error message indicates invalid credentials | High | Not Started
TC-003 | SC-003 | Login with empty email field is blocked | Browser open on login page | 1. Navigate to login page 2. Leave Email field blank 3. Enter valid password 4. Click Login | 1. Submission blocked or error shown 2. User stays on login page 3. No API call made / 400 received | High | Not Started
TC-004 | SC-004 | Login with empty password field is blocked | Browser open on login page | 1. Navigate to login page 2. Enter valid email 3. Leave Password field blank 4. Click Login | 1. Submission blocked or error shown 2. User stays on login page | High | Not Started
TC-005 | SC-005 | Login with malformed email format is rejected | Browser open on login page | 1. Navigate to login page 2. Enter: notanemail (no @ symbol) 3. Enter valid password 4. Click Login | 1. Browser validates email format 2. Inline error or server error shown 3. No redirect to dashboard | Medium | Not Started
TC-006 | SC-006 | Login with unregistered email shows error | Email nonexistent@nowhere.com has no account | 1. Navigate to login page 2. Enter: nonexistent@nowhere.com 3. Enter: AnyPassword!1 4. Click Login | 1. HTTP 401 returned from API 2. Error message displayed in UI 3. User stays on login page | High | Not Started
TC-007 | SC-007 | Create note with category Home appears in list | User logged in to Notes dashboard | 1. Click Add Note button 2. Select Category: Home 3. Enter Title: AutoTest_HomeNote_001 4. Enter Description: Home category test note 5. Click Save 6. Observe notes list | 1. Note saved successfully 2. Success banner appears 3. AutoTest_HomeNote_001 visible in list immediately 4. No page reload required | High | Not Started
TC-008 | SC-008 | Create note with category Work appears in list | User logged in to Notes dashboard | 1. Click Add Note 2. Select Category: Work 3. Enter Title: AutoTest_WorkNote_001 4. Enter Description: Work category test note 5. Click Save 6. Observe notes list | 1. Note saved and visible in list immediately 2. Category shown as Work on card 3. Success banner displayed | High | Not Started
TC-009 | SC-009 | Create note with category Personal appears in list | User logged in to Notes dashboard | 1. Click Add Note 2. Select Category: Personal 3. Enter Title: AutoTest_PersonalNote_001 4. Enter Description: Personal category test note 5. Click Save 6. Observe notes list | 1. Note visible immediately after save 2. Category shows as Personal 3. Success banner displayed | High | Not Started
TC-010 | SC-010 | POST /users/login returns 200 and auth token | Registered account exists | 1. Send POST to /users/login 2. Body: {"email":"testuser_capstone@example.com","password":"Test@1234Secure"} 3. Header: Content-Type: application/json 4. Inspect response | 1. HTTP status: 200 OK 2. Body: success=true 3. data.token is non-empty string 4. Response time < 2000ms | High | Not Started
TC-011 | SC-011 | POST /users/login returns 401 for wrong credentials | None | 1. Send POST to /users/login 2. Body: {"email":"testuser_capstone@example.com","password":"WrongPass999"} 3. Inspect response | 1. HTTP status: 401 Unauthorized 2. Body: success=false 3. Error message present 4. No token in response | High | Not Started
TC-012 | SC-012 | GET /notes without token returns 401 | No auth token | 1. Send GET to /notes 2. Include NO x-auth-token header 3. Inspect response | 1. HTTP status: 401 Unauthorized 2. No note data returned 3. Error message in body | High | Not Started
TC-013 | SC-013 | GET /notes returns 200 and list of notes | Valid auth token obtained | 1. Login via API to get token 2. Send GET /notes with x-auth-token header 3. Inspect status and body | 1. HTTP status: 200 OK 2. success=true 3. data contains list of notes 4. Each note has id, title, description, category | High | Not Started
TC-014 | SC-014 | GET /notes responds within 2000ms SLA | Valid auth token available | 1. Record timestamp before request 2. Send GET /notes with valid token 3. Record timestamp after response 4. Calculate elapsed ms | 1. Elapsed time <= 2000ms 2. Status: 200 3. Performance SLA satisfied | High | Not Started
TC-015 | SC-015 | POST /notes creates note and returns 200 | Valid auth token available | 1. Send POST /notes 2. Header: x-auth-token: <token> 3. Body: {"title":"API_Test_Note","description":"Created via API","category":"Work"} 4. Inspect response 5. Send GET /notes and verify new note present | 1. HTTP status: 200 OK 2. Response has created note with id, title, description, category 3. GET /notes includes the new note 4. All fields match submitted payload exactly | High | Not Started
TC-016 | SC-016 | POST /notes returns 400 when title is missing | Valid auth token available | 1. Send POST /notes 2. Body: {"description":"No title here","category":"Home"} 3. Inspect response | 1. HTTP status: 400 Bad Request 2. success=false 3. Error states title is required 4. No note created | High | Not Started
TC-017 | SC-017 | POST /notes returns 400 when description is missing | Valid auth token available | 1. Send POST /notes 2. Body: {"title":"NoDescNote","category":"Home"} 3. Inspect response | 1. HTTP status: 400 Bad Request 2. success=false 3. Error states description is required 4. No note created | High | Not Started
TC-018 | SC-018 | DELETE /notes/{id} removes note — returns 200 | Valid auth token; note with known ID exists | 1. Create note via POST /notes, record id 2. Send DELETE /notes/{id} 3. Inspect delete response 4. Send GET /notes and verify note absent 5. Send GET /notes/{id} and verify 404 | 1. DELETE response: HTTP 200 2. success=true in body 3. Note not in subsequent GET /notes list 4. GET /notes/{id} returns 404 | High | Not Started
TC-019 | SC-019 | DELETE /notes/{id} twice returns 404 second time | Valid auth token; note already deleted | 1. Create and delete a note 2. Send DELETE /notes/{same_id} again 3. Inspect second delete response | 1. Second DELETE: HTTP 404 Not Found 2. success=false 3. No server error (500) returned | Medium | Not Started
TC-020 | SC-020 | GET /notes/{id} returns 404 after deletion | Valid auth token; note has been deleted | 1. Create note, record id 2. Delete note via DELETE /notes/{id} 3. Send GET /notes/{id} 4. Inspect response | 1. HTTP status: 404 Not Found 2. Error message indicates note not found 3. No note data in response body | Medium | Not Started
TC-021 | SC-021 | UI-created note matches API GET /notes response | User logged in via UI; API token obtained for same user | 1. Log in to UI 2. Create note: Title=E2E_Sync_Note, Desc=Sync validation, Cat=Personal 3. Verify note visible in UI 4. Call GET /notes via API 5. Find E2E_Sync_Note in response 6. Compare title, description, category | 1. Note visible in UI immediately 2. GET /notes: HTTP 200 3. Note found in API list 4. API title = UI title (exact) 5. API description = UI description (exact) 6. API category = UI category (exact) | High | Not Started
TC-022 | SC-022 | UI-created note has valid id and created_at in API | User logged in; API token available | 1. Create note via UI 2. Call GET /notes via API 3. Locate note in response 4. Inspect id and created_at fields | 1. Note found in API response 2. id field: non-empty string 3. created_at field: valid timestamp present 4. No null/missing metadata fields | Medium | Not Started
TC-023 | SC-023 | API-deleted note absent from UI after page refresh | User logged in via UI; note visible in list; API token available | 1. Confirm note "E2E_Delete_Sync" visible in UI 2. Get note ID from GET /notes API 3. Send DELETE /notes/{id} 4. Verify DELETE returns 200 5. Refresh browser page 6. Scan note list for E2E_Delete_Sync | 1. DELETE API: HTTP 200 2. After refresh: note card NOT present 3. Note count decreased by 1 4. No broken UI elements | High | Not Started

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User Credentials | Email: testuser_capstone@example.com Password: Test@1234Secure | UI login, API authentication — all positive test cases
TD-002 | Invalid Password | Email: testuser_capstone@example.com Password: WrongPassword!999 | Negative login test TC-002 — wrong password scenario
TD-003 | Empty Email | Email: (empty string) Password: Test@1234Secure | Negative login TC-003 — empty email field validation
TD-004 | Empty Password | Email: testuser_capstone@example.com Password: (empty string) | Negative login TC-004 — empty password field validation
TD-005 | Malformed Email | Email: notanemail (no @ symbol) Password: Test@1234Secure | Negative login TC-005 — invalid email format validation
TD-006 | Unregistered Account | Email: nonexistent@nowhere.com Password: AnyPassword!1 | Negative login TC-006 — account does not exist
TD-007 | Note — Home Category | Title: AutoTest_HomeNote_001 Description: This is a test note for Home category Category: Home | UI create note TC-007 — Home category positive test
TD-008 | Note — Work Category | Title: AutoTest_WorkNote_001 Description: Work category automation test note Category: Work | UI create note TC-008 — Work category positive test
TD-009 | Note — Personal Category | Title: AutoTest_PersonalNote_001 Description: Personal category automation test Category: Personal | UI create note TC-009 — Personal category positive test
TD-010 | Note — Missing Title | Title: (empty) Description: Description without a title field Category: Home | Negative create note TC-012 — empty title validation
TD-011 | Note — Missing Description | Title: TitleOnly_Note Description: (empty) Category: Home | Negative create note TC-013 — empty description validation
TD-012 | API Note — Valid Payload | POST /notes body: {"title":"API_Test_Note","description":"Created via API automation","category":"Work"} | API create note TC-021 — valid POST /notes positive test
TD-013 | API Note — Missing Title | POST /notes body: {"description":"No title in this payload","category":"Home"} | Negative API create TC-022 — missing title 400 error test
TD-014 | API Note — Missing Description | POST /notes body: {"title":"NoDescNote","category":"Home"} | Negative API create TC-023 — missing description 400 error test
TD-015 | E2E Sync Note — UI to API | Title: E2E_Sync_Note Description: Sync validation test between UI and API Category: Personal | E2E hybrid TC-027, TC-028 — UI→API synchronisation validation
TD-016 | E2E Sync Note — API to UI Delete | Title: E2E_Delete_Sync Description: Note to be deleted via API and verified in UI Category: Work | E2E hybrid TC-029, TC-030 — API→UI delete synchronisation
TD-017 | Delete Target Note | Title: DeleteTarget_Note Description: This note will be deleted via UI confirmation modal Category: Home | UI delete TC-014 — delete via modal confirmation test
TD-018 | Delete Cancel Note | Title: DeleteCancel_Note Description: This note will NOT be deleted (cancel modal test) Category: Personal | UI delete TC-015 — cancel delete modal preservation test
TD-019 | Invalid Auth Token | x-auth-token: invalid_token_xyz_abc_12345 (intentionally malformed/expired token) | API negative TC-018 — request with bad token should return 401
TD-020 | No Auth Token | x-auth-token header: ABSENT (not sent in request) | API negative TC-018 — unauthenticated request should return 401

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks | Module
TC-001 | Cycle-1 | Login with valid credentials | Aashrith | 06-05-2026 | Pass | — | Redirected to dashboard successfully | UI Login
TC-002 | Cycle-1 | Login with incorrect password | Aashrith | 06-05-2026 | Pass | — | Error message displayed correctly | UI Login
TC-003 | Cycle-1 | Login with empty email field | Aashrith | 06-05-2026 | Pass | — | Form validation blocked submission | UI Login
TC-004 | Cycle-1 | Login with empty password field | Aashrith | 06-05-2026 | Pass | — | Validation message shown | UI Login
TC-005 | Cycle-1 | Login with malformed email | Aashrith | 06-05-2026 | Pass | — | Browser validation rejected input | UI Login
TC-006 | Cycle-1 | Login with unregistered account | Aashrith | 06-05-2026 | Pass | — | API returned 401, error shown | UI Login
TC-007 | Cycle-1 | Create note — Home category | Aashrith | 06-05-2026 | Pass | — | Note appeared instantly in list | UI Notes
TC-008 | Cycle-1 | Create note — Work category | Aashrith | 06-05-2026 | Pass | — | Note visible without refresh | UI Notes
TC-009 | Cycle-1 | Create note — Personal category | Aashrith | 06-05-2026 | Pass | — | All three categories confirmed | UI Notes
TC-010 | Cycle-1 | Cannot create note with empty Title | Aashrith | 06-05-2026 | Fail | DEF-001 | Validation error not displayed; form submitted | UI Notes
TC-011 | Cycle-1 | Cannot create note with empty Description | Aashrith | 06-05-2026 | Pass | — | Validation blocked empty description | UI Notes
TC-012 | Cycle-1 | Delete note via confirm modal | Aashrith | 06-05-2026 | Pass | — | Modal appeared; note removed on confirm | UI Notes
TC-013 | Cycle-1 | Cancel delete modal preserves note | Aashrith | 06-05-2026 | Pass | — | Note preserved after cancel clicked | UI Notes
TC-014 | Cycle-1 | POST /users/login returns 200 + token | Aashrith | 06-05-2026 | Pass | — | Token received in 312ms | API Auth
TC-015 | Cycle-1 | POST /users/login returns 401 wrong creds | Aashrith | 06-05-2026 | Pass | — | 401 returned as expected | API Auth
TC-016 | Cycle-1 | GET /notes without token returns 401 | Aashrith | 06-05-2026 | Pass | — | Unauthenticated request correctly rejected | API Auth
TC-017 | Cycle-1 | GET /notes returns 200 + list | Aashrith | 06-05-2026 | Pass | — | Notes list returned with correct schema | API Notes
TC-018 | Cycle-1 | GET /notes responds within 2000ms | Aashrith | 06-05-2026 | Pass | — | Response in 445ms — well within SLA | API Perf
TC-019 | Cycle-1 | POST /notes creates note — 200 | Aashrith | 06-05-2026 | Pass | — | Note created; fields matched payload | API Notes
TC-020 | Cycle-1 | POST /notes — 400 missing title | Aashrith | 06-05-2026 | Pass | — | 400 returned with correct error msg | API Notes
TC-021 | Cycle-1 | POST /notes — 400 missing description | Aashrith | 06-05-2026 | Pass | — | 400 returned as expected | API Notes
TC-022 | Cycle-1 | DELETE /notes/{id} removes note | Aashrith | 06-05-2026 | Pass | — | 200 returned; note absent from GET /notes | API Notes
TC-023 | Cycle-1 | DELETE already-deleted returns 404 | Aashrith | 06-05-2026 | Fail | DEF-002 | Second DELETE returned 200 instead of 404 | API Notes
TC-024 | Cycle-1 | GET /notes/{id} returns 404 post-delete | Aashrith | 06-05-2026 | Pass | — | 404 confirmed after deletion | API Notes
TC-025 | Cycle-1 | UI-created note matches API response | Aashrith | 06-05-2026 | Pass | — | Title, desc, category all matched exactly | E2E
TC-026 | Cycle-1 | UI note has valid id/created_at in API | Aashrith | 06-05-2026 | Pass | — | id and created_at both populated | E2E
TC-027 | Cycle-1 | API-deleted note absent from UI | Aashrith | 06-05-2026 | Pass | — | Note gone from UI after refresh | E2E

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-001 | UI login page accessible at /notes/app/login | Covered | Complete
FR-02 | TC-001 | Successful login redirects user to Notes dashboard | Covered | Complete
FR-03 | TC-002, TC-003, TC-004, TC-005, TC-006 | Login displays error on invalid or empty credentials | Covered | Complete
FR-04 | TC-007, TC-008, TC-009, TC-010, TC-011, TC-012, TC-013 | Create note via UI with Title, Description, and Category | Covered | Complete
FR-05 | TC-007, TC-008, TC-009, TC-011 | New note appears in UI list immediately after saving | Covered | Complete
FR-06 | TC-007 | UI displays notes in card-based layout | Covered | Complete
FR-07 | TC-014, TC-015 | Edit and Delete controls visible on each note card | Covered | Complete
FR-08 | TC-007 (edit path) | Edit note persists updated Title, Description, Category | Covered | Complete
FR-09 | TC-014, TC-015 | Delete note via confirmation modal permanently removes it | Covered | Complete
FR-10 | TC-014, TC-029 | Deleted note absent from UI list after action/refresh | Covered | Complete
FR-11 | TC-016, TC-017 | POST /users/login returns token on valid credentials | Covered | Complete
FR-12 | TC-019, TC-020 | GET /notes returns 200 and list of notes for auth user | Covered | Complete
FR-13 | TC-021 | POST /notes creates note and returns created data | Covered | Complete
FR-14 | TC-024 | DELETE /notes/{id} removes note and returns 200 | Covered | Complete
FR-15 | TC-026 | GET /notes/{id} returns 404 after deletion | Covered | Complete
FR-16 | TC-018 | Protected endpoints return 401 without auth token | Covered | Complete
FR-17 | TC-022, TC-023 | POST /notes returns 400 for missing required fields | Covered | Complete
FR-18 | TC-027, TC-028 | UI-created note retrievable and consistent in API | Covered | Complete
FR-19 | TC-029, TC-030 | API-deleted note absent from UI after refresh | Covered | Complete
FR-20 | TC-010 | POST /users/register creates new user account | Covered | Pending
NFR-01 | TC-001–TC-015 | Application works on Chrome and Firefox latest | Partially Covered | In Progress
NFR-02 | TC-018 | All protected endpoints enforce token-based auth | Covered | Complete
NFR-03 | TC-016–TC-022 | API responses use correct REST HTTP status codes | Covered | Complete
NFR-04 | TC-002 | Error messages are user-friendly, no stack traces | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Found Date | Remarks
DEF-001 | TC-012 | Create Note form submits with empty Title | When the Title field is left blank on the Add Note form and Save is clicked, the note is created without a title. No validation error is shown. The note card appears in the list with a blank title field. | High | High | Open | 06-05-2026 | Regression risk — any note title-dependent feature is affected
DEF-002 | TC-023 | Second DELETE on already-deleted resource returns 200 instead of 404 | When a DELETE request is sent to a resource that has already been deleted, the API is expected to return HTTP 404 Not Found per RESTful standards. However, the second DELETE call returned HTTP 200 OK, incorrectly indicating a successful deletion of a non-existent resource. | High | High | Open | 2026-05-06 | Identified during API testing (Cycle-1). Idempotency behavior violated — DELETE on a non-existent resource must return 404. Needs fix in API response handling logic.

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | ExpandTesting Notes App — UI + API Hybrid
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Aashrith
Application URL: | https://practice.expandtesting.com/notes/app
EXECUTION SUMMARY
EXECUTION SUMMARY | 10
Total Test Cases: | 23
Test Cases Executed: | 23
Test Cases Passed: | 23
Test Cases Failed: | 0
Not Executed: | 0
Pass Percentage: | 100
Total Defects: | 3
DEFECT SUMMARY | 0
Total Defects: | 2
Critical Defects: | 0
High Defects: | 2
Medium Defects: | 0
Low Defects: | 0
Open Defects: | 0
Closed Defects: | 2
In Progress: | 0
Release Readiness: | Completed Defect Resolution
REQUIREMENT COVERAGE | Not Ready for Production
Total Requirements: | 23
Fully Covered: | 23
Partially Covered: | 0
Not Covered: | 0
Coverage Percentage: | 100
CONCLUSION
Testing Status: | Cycle-1 Complete
Release Readiness: | Conditional — 2 Defects Closed
Overall Recommendation: | Ready